## RunSummary
Evidence item | Value | Source
Generated UTC date | 2026-08-14 | generate_fpr_evidence.py
Images covered | 1200 | result CSV image_id values
Transform categories | 12 | transforms.py
Hash rows | 768000 | hash_robustness_results.csv
TrustMark rows | 97200 | trustmark_robustness_results.csv
LSB rows | 97200 | lsb_robustness_results.csv
DCT rows | 97200 | dct_robustness_results.csv
Interpretation | Descriptive benchmark; image is the experimental unit | methodology

## MethodSummary
Transform | TrustMark mean bit accuracy | LSB mean bit accuracy | DCT mean bit accuracy
brightness | 0.96961 | 0.4974 | 0.86944
contrast | 0.96505 | 0.50546 | 0.8748
crop_center | 0.65487 | 0.49871 | 0.50077
crop_random | 0.64553 | 0.50054 | 0.50132
gaussian_blur | 0.96776 | 0.58453 | 0.82318
jpeg_compression | 0.90443 | 0.50902 | 0.83283
letterbox | 0.56196 | 0.64517 | 0.63597
rotation | 0.64378 | 0.61594 | 0.54973
salt_pepper_noise | 0.85955 | 0.96847 | 0.74168
saturation | 0.99229 | 0.5867 | 0.9032
scaling | 0.99414 | 0.51298 | 0.5021
vibrancy | 0.96869 | 0.70367 | 0.89237

## Gantt
Work package | Start | Finish | Status | Evidence
Requirements and literature review | 2026-02-01 | 2026-03-15 | Complete | Report literature chapter
Transform pipeline and baselines | 2026-03-16 | 2026-04-30 | Complete | transforms.py and baseline scripts
TrustMark integration and metric correction | 2026-05-01 | 2026-05-31 | Complete | trustmark_robustness.py
100-image pilot and debugging | 2026-06-01 | 2026-06-30 | Complete | current CSVs and validation
1,200-image final benchmark | 2026-08-10 | 2026-08-17 | In progress | run_1200_experiment.log
Statistical analysis and figures | 2026-08-17 | 2026-08-22 | Pending | analysis scripts and figures
FPR writing, proofreading, packaging | 2026-08-22 | 2026-08-31 | Pending | FPR and submission manifest

## RiskRegister
Risk | Probability | Impact | Rating | Mitigation | Contingency | Owner | Status
Disk exhaustion during benchmark | Medium | High | High | Run serially, avoid persistent artefacts, monitor storage | Resume from flushed CSV checkpoint | Student | Open
Incomplete or duplicated result rows | Medium | High | High | Manifest, expected-row and duplicate-key validator | Reject run and rerun affected pipeline | Student | Controlled
Non-reproducible stochastic transform | Low | High | Medium | Stable SHA-256 seed and recorded manifest | Regenerate affected rows | Student | Controlled
Overclaiming authenticity | Medium | High | High | Separate similarity, watermark recovery and provenance claims | Restrict conclusion to tested signals | Student/Supervisor | Open
Dataset/dependency licensing uncertainty | Low | High | Medium | Use official terms and do not redistribute source images | Replace dataset or obtain permission | Student | Open
Dashboard/database integration incomplete | Medium | Medium | Medium | Describe CSV-backed prototype accurately | Keep production integration as future work | Student | Controlled

## ObjectiveMap
Objective | Method | Evidence | Result/status | FPR section
Review literature and standards | Structured review of official post-2019 sources | Final report references and synthesis | Complete | Literature Review
Implement deterministic transforms | Shared Pillow transform module | transforms.py, manifest, stable seed | Complete | Methodology
Evaluate neural watermark | TrustMark encode/decode matrix | trustmark_robustness_results.csv | Complete for validated sample | Results
Compare perceptual hashes | Eight hash variants and Hamming distance | hash_robustness_results.csv | Complete for validated sample | Results
Compare classical baselines | LSB and DCT reference implementations | lsb/dct CSVs | Complete for validated sample | Results
Analyse complementary signals | Threshold and ensemble analysis | ensemble_decision_matrix.csv | Descriptive only; not calibrated production auth | Evaluation
Run payload/ECC ablation | 12-config dev sweep; selected config at 1,200 | payload_ecc_ablation_dev100.csv, payload_ecc_ablation_selected_final1200.csv | Dev 97,200 rows; final 97,200 rows; validated | Evaluation/Future work
Deliver usable artefact | CSV-backed dashboard prototype | dashboard files and smoke test | Prototype complete; database not validated | Implementation appendix

## PayloadECC
Scale | config | n | TM exact% | ensemble% | hash rescue pp | source
dev100 | bch_3_1chars | 8100 | 50.28 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_3_4chars | 8100 | 59.12 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_3_5chars | 8100 | 60.22 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_4_1chars | 8100 | 58.06 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_4_4chars | 8100 | 61.53 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_4_5chars | 8100 | 61.72 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_5_1chars | 8100 | 58.09 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_5_4chars | 8100 | 63.09 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_5_5chars | 8100 | 62.73 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_super_1chars | 8100 | 64.8 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_super_4chars | 8100 | 66.36 |  |  | payload_ecc_ablation_dev100.csv
dev100 | bch_super_5chars | 8100 | 66.02 |  |  | payload_ecc_ablation_dev100.csv
final1200 | bch_super_4chars | 97200 | 66.22 | 89.36 | +23.14 | payload_ecc_ablation_selected_final1200.csv + ensemble_aware_payload_final1200.md